meeting: Future of Work Methodology Brainstorm date: 2025-09-08 attendees: - Leilah Gagnon - Evan Thomas tags: - Future of work - FoW - brainstorming - SMC summary: | Our conversation began to strategize what concrete and realistic deliverables would be for the project. Similarly open-ended projects had issues with scope-creep and political-reframing. Fortunately there is a hard deadline and deliverable that will help guide us, an SMC presentation on November 12 or 16.

Challenges for the developing a methodology for analysis include non-alignment between the GSBPM and the established HR processes interacting with work descriptions. Moreover, work-descriptions are flexible definitions and so mappings between changes to GSBPM have multiple (contradictory) interpretations for work descriptions should be changed. Furthermore, with such a short timeline for the project there is little time for consultation, collaboration or research. Our recommendations should also align with our international statistical office partners. There are few existing examples of similar project attempts that might be leveraged as examples for the LLM’s analysis. However, what we present to SMC may be limited to a proof of concept and a roadmap for incorporating consultation, quality assurance, and international alignment into the project deliverables.

The conversation turned to what inputs, outputs, and intermediate forms would be appropriate for our methodology. In discussion with the LLM, we expect to begin by structuring the direction given to the fields (eg. “A glimpse of the future” from “Tier 2 Committee Visions for the future of the agency”). The implementations produced by various fields would be mined by the LLM to populate this structure. Common elements among structured field plans will provide insight into what items of the GSBPM are most targeted. It can be assumed that the most targeted areas are also the most in-need of revision.

LG identified case-studies as possible integrity tests for the LLM methodology. She also suggested focusing on particular work descriptions such as “EC-03 Operations Coordinator (700-202)”, “EC-02 Data Production and Dissemination Officer (900-218)”, and “EC-01 Recruit (900-200)”.

The next step in developing the methodology is to draw a process diagram, illustrating inputs, outputs, and processing.

background: - topic: Objective, Deliverables and low hanging fruit. summary: > The deliverable is a deck for Saeid’s SMC presentation on Nov 12/16. Appropriate intermediate documents may provide low-hanging-fruit, as well as utility for QA. details: objectives: - item: SMC “pre-endorsement” of work. deliverables: - item: SMC deck

- item: Deck summaries
      description: |
        SMC decks could be consolidated in to a brief that summarizes the findings
        of each field.
      value:
        - Useful for SM brief

    - item: JSON of each field's contribution/implementation
      value:
        - uniform format (QA)
        - intermediate representation

- topic: Project Phases background: null details:

  - item: SM proposal description: |

    - Environmental setup

    - Data-driven updates to GSBPM

    - Mapping updated GSBPM to future activities and skills gaps.

  - item: LG proposal for SSC intake summary: |

    - Environmental scan and research (3 months)

    - Analysis and Mapping of GSBPM processes (3 months)

    - Mapping GSBPM to current work descriptions (3 months)

    - Mapping key activities to substitute requirements (3 months) details:

    - item: 1) Environmental scan and research (3 months) summary: null details:

      - Research and analysis of literature related to NSOs.

      - Intake of various academic articles.

      - Summarization and analysis and structuring of information and data.

      - Extraction of trends, themes.

      - Review of historical evolution on topics by date of publication.

    - item: 2) Analysis and Mapping of GSBPM Processes (3 months) summary: null background: > GSBPM (Generic Statistical Business Process Model) is an international framework outlining the core statistical processes. The framework will serve as a baseline for assessing transformation. details:

      - Review and analyze of all the business processes listed.

      - Review and identification of those that involve manual collection, processing, etc.

    - item: 3) Mapping GSBPM to current work descriptions (3 months) summary: null details:

      - Review and mapping of these processes against work description key activities (unclassified data in a database PCIS and internal StatCan repository of job descriptions

      - Identify gaps between requirements and work descriptions

      - Identify gaps between skills and existing work descriptions

    - item: 4) Mapping key activities to substitute requirements (3 months) summary: null details:

      - Review and map these key activities that identify manual or repetitive activities

      - Identify forward facing requirements linked to information obtained via the literature review Part 1. outstanding: &outstandingPhases4

      - question: Specifically what “substitute requirements”? answer: null

      - question: What are the “substitute requirements” substituting? answer: Those requirements imposed by the GSBPM.

- topic: Identifying data sources for context, input, direction, or testing. summary: | In determining a methodology we can yield summaries for many of the provided sources. Doing so should assist in

- LG presented the following as (roughly) the hierarchy of importance of our data sources.

- 1. GSBPM
2. Strategic priority deck (this is the "WHAT")
3. Program area input
4. Top core areas and themes (ideally case-study tests)
5. Generic work descriptions (Test)

- The last of these, Generic work descriptions, may be useful for quality assurance by comparing them with the case studies. details: style: - item: SMC presentations value: > Using LLM we can determine the overall structure of these presentations, and can identify the importance of elements by comparing the content to the feedback provided. All of this is available on the intranet. (This is an alternative to using the HR SMC template). - item: HR SMC template value: > HR has the subject matter expertise that is closest to what we are attempting to do. Using their template for SMC presentations might be helpful in structuring our presentation deliverable. (This is an alternative to deriving an SMC template from published SMC presentations). context: - item: !specify processes background: !fill null value: !fill null - item: !specify directives background: !fill null value: > identify which elements of GSBPM are appropriate for automation or AI-assistance. - item: Artificial intelligence Impact Assessments (AIA) value: !fill null - item: Skills gap assessment background: !fill null value: !fill null - item: OECD publication, “Common Human Resources Business Process (CHRBP)” background: > Publication that intended to standardize HR business processes across GoC. Seems to have disappeared. value: !validate Document has similar objectives? - item: PSMAC publication background: !fill null value: !validate “A previous attempt for what we’re doing to do now” inputs: description: > item-wise data, these items will be individually processed to yield data extract, summary, transformation or generation. These items may be used at distinct steps of the analysis, and even used repeatedly. items: - item: Field feedback of GSBPM key changes. background: !fill null value: > Extract elements from field feedback to identify common elements, and strategize for areas of revision. - item: work descriptions background: > Two categories of work descriptions are kept, generic work-descriptions are kept public, and unique work descriptions (for one-off employment) are kept in a private repository maintained by “our classification folks”. value: - trend analysis on unique work descriptions, analyzing trends of core activities (inferred by the responsibilities or skills listed). - !deliverable Proposed changes to generic work-descriptions, following from the forecasted changes to GSBPM. - item: Case studies from “StatCan 2030 EBA Platforms Update SMC” value: > These case studies should be readily produced by the LLM following our methodology. Although LLM output might not be identical it is a litmus test to evaluate the methodology against expected results. outstanding:

- What about Field 6?

- Would having information about field 6 constitute a CoI? todo:

- Finalize notes.

- Develop workflow architecture and flowchart.

- Draft project plan. raw: |

- Refine milestones for SSC env application.

  - Review

- Looking pin-down the ask.

  - Concrete outputs

  - What does sucess look like.

  - Want to avoid the scope-creep (political reframing) with the prior IP.

  - The ask is a bit unrealistic -> first project into something realistic.

- Deliverable IS A DECK. (we have that deck for SMC)

  - There expecations for content such as:

    - include what is in our control, but exclude what is not.

      - (not excluded.. but as a sort of “crossed-out” line).

- Work after the deck (for Stratectic Management Committee (SMC))

- work breakdown structure: (step 1,2,3,4,5) generic occupational group standards: ITs specific work descriptions that pull from the group/classifications

  - unique (kept in a private repository by our classification people). - Might see evolution in these since these are custom

  - generic (saved in a system)

    - DS one is most up to date.

- GSPPM is very similar to HR business processes (very hierarchical)

  - broken down (eg)

    - planning

      - forecasting

- the process and the key activities don’t follow the same logical~flow

  - See OECD publication..

  - See PSMAC publication for a previous attempt for what we’re trying to do now (within HR)

    - Looking to reduce “time-to-staff” by optimization _____

  - ALSO CHECK WITH OTHER STATISTICAL OFFICES FOR WHAT THEY ARE DOING.

- GSPPM

  - LG idea: collection & processing.

- Start with “one” that is known (for mapping)

  - see chat

- MAPPING TO WORK-DESCRIPTIONS.

- Directives include in the prompt, to indentify what elements are appropriate to do, and what aren’t.

- Low-hanging fruit

  - Summarize SMC decks (SM has recieved alot).

- INS

  - undertand processes

  - understand diretives

  - understand AIAs

  - Skills gap assesment.

- Then

  - Highlight key areas of focus (of the above/ inline with the above).

- “Variety of how we define the work makes the mapping difficult”.

- A Work description includes key tasks, but is not exhaustive.. and are out of date. (less 80% doesn’t have to align with work description).

- informal conversation w/ external partners (national statistics offices) for sanity check.

- PULL SMC PRESENTATIONS FOR COMMON STYLE.

  - or adhere to SME template (HR has one)

  - or adhere to “most sucessful” template.

  - Ensure to include where each theme comes from.

  - Break sources down into different meaningful information products.

  - Start with direction provided…

1. GSBPM

- Keep provided case studies as test items.

- What about field 6~

- SMC OBJECTIVE

  - PRE-ENDORSEMENT

- Sub-elements

  - See intake form.